## DevForum
| DevForum |  | Total hrs: 7 days * 7 developers * 0.7 = 34 days
SPRINT 1
SR. NO. | STORY | ESTIMATION IN DAYS | PRIORITY | OWNED BY | TESTED BY | 2022-08-30 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
1 | Logins a user | 2 | 1 | Divya |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 1.5
2 | Logs out a user | 2 | 1 | Ch.Bhagya Sri |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
3 | Registers an user | 2 | 1 | P.Bindu Madhavi |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 1.5
4 | Validates the client’s token | 2 | 1 | K.Akhil |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
5 | Create new question category | 1.5 | 1 | Yogendra D |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1
6 | Returns all categories | 1.5 | 1 | V. Bharath |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1
7 | Returns category by id | 1.5 | 1 | sravya kalluri |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
8 | Deletes an existing category | 1.5 | 1 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
9 | Returns user information | 1.5 | 2 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
10 | Developer can post technical problem on dev forum. | 2 | 2 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
11 | Returns list of all questions posted by logged in user | 2 | 2 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
12 | Updates the question | 2 | 2 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
13 | Delete the question | 1.5 | 2 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
14 | Update an existing category | 1.5 | 2 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
15 | Returns list of all questions by category | 1.5 | 2 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
16 | Reply to a question | 2 | 3 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
17 | Other users also can like, dislike on specific question. | 1.5 | 3 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
18 | Searches questions by search text | 3 | 3 |  |  | 2022-08-30: 3; 2022-09-01: 3; 2022-09-02: 3
19 | Returns question list by tag name | 2 | 3 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
| Total estimated: | 34.5 |  |  | Total remaining | 2022-08-30: 34.5; 2022-09-01: 34.5; 2022-09-02: 32.5

## InterviewManagement
| Interview Management |  | Total hrs: 7 days * 7 developers * 0.7 = 34 days
SPRINT 1
SR. NO. | STORY | ESTIMATION IN DAYS | PRIORITY | OWNED BY | TESTED BY | 2022-08-30 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
1 | Logins a user | 2 | 1 | Amrutha |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
2 | Logs out a user | 2 | 1 | Deekshita |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
3 | Registers a panel member | 2 | 1 | Ashritha |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
4 | Returns user information | 1.5 | 1 | Rehaan |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1
5 | Validates the client’s token | 2 | 1 | Akshansh |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
6 | Adds new candidate | 2 | 2 | Aditya |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 1.5
7 | View candidate by id | 1.5 | 2 | Arikaran |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1
8 | Adds a panel member | 2 | 2 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
9 | Lists all panel members | 1.5 | 2 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
10 | Search employees by name | 2 | 2 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
11 | Schedule an interview | 2 | 3 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
12 | Shares a candidate for interview with panel member | 2 | 3 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
13 | Delete a panel member | 1.5 | 3 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
14 | Search employees by skill | 2 | 3 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
15 | View interview candidates assigned to the technical panel member | 1.5 | 3 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
16 | View interview candidate by interviewId | 1.5 | 3 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
17 | View interview candidates assigned to the HR panel member | 1.5 | 3 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
18 | Update an interview | 2 | 4 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
19 | Give technical rating to the candidate | 1.5 | 4 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
20 | Surrender as panel member | 1.5 | 4 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
21 | Give HR rating to the candidate | 1.5 | 4 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
| Total remaining: | 37 |  |  |  | 2022-08-30: 37; 2022-09-01: 37; 2022-09-02: 35.5

## TalentPortal
| Talent Portal |  | Total hrs: 7 days * 7 developers * 0.7 = 34 days
SPRINT 1
SR. NO. | STORY | ESTIMATION IN DAYS | PRIORITY | OWNED BY | TESTED BY | 2022-08-30 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09
1 | Login as User or Admin | 2 | 1 | Aseesh |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 1.5
2 | Logs out a user/admin | 2 | 1 | Vignika |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
3 | Registers an user | 2 | 1 | Saketh |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 1.5
4 | Returns user information | 1.5 | 1 | Ashruff |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
5 | Validates the client’s token | 2 | 1 | Bhavya |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
6 | Posting a new job | 2 | 1 | Aishwarya |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
7 | Post a job application in the portal | 2 | 2 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
8 | Searches jobs as per searchText | 2 | 3 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
9 | Get Job application status | 1.5 | 3 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
10 | List of all jobs in the portal | 1.5 | 3 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
11 | Reads all jobs posted by logged in user | 1.5 | 3 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
12 | Matches jobs using the peovided 'searchText' within all fields of skill | 2 | 3 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
13 | Get list of all jobs applied | 1.5 | 4 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
14 | Updates an existing Job | 2 | 4 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
15 | Update a job application status | 2 | 4 |  |  | 2022-08-30: 2; 2022-09-01: 2; 2022-09-02: 2
16 | Deletes specific job posted by logged in user | 1.5 | 4 |  |  | 2022-08-30: 1.5; 2022-09-01: 1.5; 2022-09-02: 1.5
| Total remaining: | 29 |  |  |  | 2022-08-30: 29; 2022-09-01: 29; 2022-09-02: 28

## Exam Portal
| Exam Portal |  | Total hrs: 7 days * 7 developers * 0.8= 39 days
SPRINT 1
SR. NO. | STORY | ESTIMATION IN DAYS | PRIORITY
1 | Logs in a user | 2 | 1
2 | Logs out a user | 2 | 1
3 | Registers an user | 2 | 1
4 | Returns user information | 2 | 1
5 | Validates the client’s token | 2 | 1
6 | Create new question | 2 | 1
7 | get all questions | 2 | 1
8 | get question by id | 1 | 1
9 | update question by id | 2 | 2
10 | delete question | 1 | 2
11 | Create question group | 2 | 2
12 | Get question groups | 2 | 2
13 | Returns particular question group based on id | 2 | 2
14 | Update the question group based on group id | 2 | 2
15 | Delete a question group based on question id | 2 | 2
16 | Create a quiz | 2 | 3
17 | Get all quizzes | 1 | 3
18 | Get a particular quiz | 2 | 3
19 | Delete a particular quiz | 1 | 3
20 | Update quiz | 2 | 3

## Technical Blogging
Technical Blog
SPRINT 1
Sr No | STORY | Estimation in days | Priority
1 | Create new blog | 2 | 1
2 | get all blogs rest api | 1.5 | 1
3 | get blog by id | 1.5 | 1
4 | update blog by id rest api | 2 | 1
5 | delete blog rest api | 1.5 | 1
6 | Registers an user | 2 | 2
7 | Adding comment to particular Blog | 2 | 2
8 | Get a comment for particular blog | 1.5 | 2
9 | Get a particular comment for particular blog | 1.5 | 2
10 | Update particular comment for particular blog | 2 | 2
11 | Delete a particular comment for particular blog | 1.5 | 2
12 | Returns user information | 1.5 | 3
13 | Validates the client’s token | 2 | 3
14 | Logins a user | 2 | 4
15 | Logs out a user | 2 | 5

## Panel Management
Panel Management
SPRINT 1
Sr No | STORY | Estimation in days | Priority
1 | Slot for 1hour can be created and store in database | 2 | 1
2 | Returns list of available slots | 1.5 | 1
3 | Updates the slot | 2 | 1
4 | Delete the slot | 1.5 | 1
5 | Create Panel Master where panel to be added | 2 | 2
6 | Returns list of panels | 1.5 | 2
7 | Updates the panel | 2 | 2
8 | Delete the panel | 1.5 | 2
9 | Get Skill wise slots (even if any skill matches) | 1.5 | 3
10 | Get highest slot provider – Count slots and whichever is max | 1.5 | 3
11 | Get unused slots | 1.5 | 3
12 | Logins a user | 2 | 4
13 | Registers a user | 2 | 4
14 | Returns user information | 1.5 | 4
15 | Validates the client’s token | 2 | 4
16 | Logs out a user | 2 | 5